## Backlog
UC ID | Module | Owner | Actor | Use Case | Status | Deadline | Difficulty | Description | Notes
UC-01 | Account & Customer Status | BonVT | Guest | Register account | Done | 2026-05-10 | Medium | A guest creates a customer account. | Unique email and phone are enforced. Customer is the default role. SMTP email verification is an extension of registration.
UC-02 | Account & Customer Status | BonVT | Guest/User | Login | Done | 2026-05-10 | Medium | A user logs in to the system. | JWT login supports email or phone. Only status = active may sign in; status = locked or inactive is rejected. Customer lock also revokes existing JWTs.
UC-03 | Account & Customer Status | BonVT | User | Logout | Done | 2026-05-10 | Low | A user logs out of the system. | Logout revokes the active JWT so the same token cannot be reused.
UC-04 | Account & Customer Status | BonVT | User | Manage personal profile | Done | 2026-05-10 | Medium | A user views and updates their personal information. | Users may update only their own name, phone, and address. Role and account status are administrative data and are never editable from the personal profile.
UC-05 | Account & Customer Status | BonVT | User | Change password | Done | 2026-05-10 | Medium | A logged-in user changes their password. | The current password is required, the replacement must satisfy password rules, and each user may change only their own password.
UC-06 | Account & Customer Status | BonVT | Guest/User | Forgot/reset password | Done | 2026-05-10 | Medium | A user resets a forgotten password. | Reset/setup tokens expire after one hour and are single-use. Actual mailbox receipt remains an external SMTP smoke check.
UC-07 | Account & Customer Status | BonVT / BaoNG | Admin | View and lock/unlock customer accounts | Done | 2026-05-10 | Medium | An admin views Customer account and activity information in read-only mode, then locks or unlocks sign-in access when required. | Only View and Lock/Unlock are exposed; Customer profile editing is unavailable. Lock requires a reason, sets status = locked as the single database source of truth, revokes active tokens, and sends email/in-app notification. Unlock restores status = active and sends restoration notifications.
UC-08 | Account & Customer Status | BonVT | Admin | Manage staff accounts | Done | 2026-05-10 | Medium | An admin creates and maintains Staff identity/status; Staff receives an invitation to set their own password. | Admin creates and updates Staff identity/status only. A one-hour setup link is emailed so Staff owns the password; Admin cannot set or replace it.
UC-09 | Account & Customer Status | BonVT | Admin | View customer activity status | Done | 2026-05-10 | Low | Admin views customer activity information. | Activity is derived from the Customer booking history, completed count, and reported issues. The endpoint and UI are Admin-only.
UC-10 | Field, Slot, Service & Issue Management | BaoNG | Guest/Customer | View field list | Done | 2026-05-10 | Low | A guest or customer views the list of available football fields. | Only active fields are customer-visible. Field type, location, surface, capacity, image, and pricing context are shown.
UC-11 | Field, Slot, Service & Issue Management | BaoNG | Guest/Customer | View field detail | Done | 2026-05-10 | Low | A guest or customer views detailed information about a selected field. | Includes uploaded image, location, surface, capacity, price range/bands, and active add-ons. Reviews/ratings are explicitly out of scope.
UC-12 | Field, Slot, Service & Issue Management | BaoNG | Customer | Search available fields by date/time | Done | 2026-05-10 | High | A customer searches for available fields by date, time, and field type. | Search filters by playing date, field type, and field. Booked, blocked, expired, and past slots are excluded.
UC-13 | Field, Slot, Service & Issue Management | BaoNG | Admin | Manage football fields | Done | 2026-05-10 | Medium | An admin creates, updates, enables, or disables football fields. | Admin creates/updates fields, changes active status, and uploads JPEG/PNG/WebP/GIF images up to 5 MB.
UC-14 | Field, Slot, Service & Issue Management | BaoNG | Admin | Manage field pricing by time range | Done | 2026-05-10 | High | An admin configures field prices by time range and day type. | Pricing supports weekday/weekend and time bands. The applicable price is resolved for each generated slot.
UC-15 | Field, Slot, Service & Issue Management | BaoNG | Staff | Manage unavailable slots | Done | 2026-05-10 | High | Staff blocks slots that cannot be booked. | Staff blocks and unblocks slots with a reason. Blocked slots are removed from customer availability.
UC-16 | Field, Slot, Service & Issue Management | BaoNG | Staff | View field operation calendar | Done | 2026-05-10 | Medium | Staff views the operation calendar by field and date. | Daily operations show available, blocked, and booked slots with booking/customer context.
UC-17 | Field, Slot, Service & Issue Management | BaoNG | Admin | Manage extra services | Done | 2026-05-10 | Medium | An admin manages extra services such as ball rental, bibs, drinks, or referee service. | Admin creates, updates, activates, and deactivates priced rental, sale, or staff services.
UC-18 | Field, Slot, Service & Issue Management | BaoNG | System/Customer | Check extra service availability | Done | 2026-05-10 | Medium | The system checks whether selected extra services are available. | Max-per-booking and stock are validated across overlapping active bookings so shared inventory is not overbooked.
UC-19 | Field, Slot, Service & Issue Management | BaoNG | Customer/Staff | Add extra services to booking | Done | 2026-05-10 | Medium | Customer or staff adds extra services to a booking. | Selected services are priced in checkout and persisted in booking totals and invoice line amounts.
UC-20 | Field, Slot, Service & Issue Management | BaoNG | Customer/Staff | Update extra services before check-in | Done | 2026-05-10 | Medium | The owning customer or Staff updates selected extra services before check-in. | Owning Customer or Staff may edit before check-in. Services, discounts, balance/refund delta, and invoice are recalculated atomically.
UC-21 | Field, Slot, Service & Issue Management | BaoNG | Customer/Staff | Report field/service issue | Done | 2026-05-10 | Medium | Customer or staff reports a field or service issue. | An issue may reference a field, booking, or extra service and is visible to the relevant operations workflow.
UC-22 | Field, Slot, Service & Issue Management | BaoNG | Staff | Resolve field/service issue | Done | 2026-05-10 | Medium | Staff handles and updates the issue status. | Staff assigns/updates status, records resolution notes, and resolution produces the reporter notification.
UC-23 | Booking Lifecycle | NgocPA | Customer | Create online booking | Done | 2026-05-10 | High | A customer creates an online field booking. | Customer-only online flow validates availability, pricing, promotion/membership rules, payment hold, and PayPal Sandbox checkout.
UC-24 | Booking Lifecycle | NgocPA | Staff | Create walk-in booking | Done | 2026-05-10 | Medium | Staff creates a booking for a customer who comes directly to the venue. | Staff creates the walk-in booking for an existing customer and records cash deposit, full, or remaining payment at the venue.
UC-25 | Booking Lifecycle | NgocPA | Customer/Staff | View booking detail | Done | 2026-05-10 | Low | A user views detailed information about a booking. | Detail includes slot, services, promotion, payments, invoice, and refunds. Access is protected by role and ownership.
UC-26 | Booking Lifecycle | NgocPA | Customer | View my bookings | Done | 2026-05-10 | Low | A customer views their current and past bookings. | The Customer Account workspace shows current/past bookings and their billing details.
UC-27 | Booking Lifecycle | NgocPA | Staff | View booking calendar | Done | 2026-05-10 | Medium | Staff views bookings by field and date. | The Staff workspace provides a daily booking queue/calendar and selected-booking operation controls.
UC-28 | Booking Lifecycle | NgocPA | System/Staff | Confirm booking | Done | 2026-05-10 | High | A booking is confirmed after valid payment or staff approval. | A valid captured payment may confirm the booking; Staff may confirm an eligible pending request.
UC-29 | Booking Lifecycle | NgocPA | Staff | Reject booking request | Done | 2026-05-10 | Medium | Staff rejects an invalid pending booking request. | Only pending bookings can be rejected by Staff.
UC-30 | Booking Lifecycle | NgocPA | Customer/Staff | Reschedule booking | Done | 2026-05-10 | High | Customer or Staff moves a booking to another available field slot. | The new slot must be free. Existing payment history is preserved and the new price creates either a balance due or refundable delta.
UC-31 | Booking Lifecycle | NgocPA | Customer/Staff | Preview cancellation fee/refund | Done | 2026-05-10 | Medium | Before cancellation, the user previews the cancellation fee and refundable amount. | Cancellation preview is a required first step before confirmation and displays the policy-derived refundable amount.
UC-32 | Booking Lifecycle | NgocPA | Customer/Staff | Cancel booking | Done | 2026-05-10 | High | A booking is cancelled according to the cancellation policy. | Pending/confirmed bookings may be cancelled after preview. Checked-in/completed bookings cannot be cancelled; eligible refunds enter workflow.
UC-33 | Booking Lifecycle | NgocPA | Staff | Check-in booking | Done | 2026-05-10 | Medium | Staff confirms that the customer has arrived at the venue. | Only confirmed bookings can be checked in by Staff.
UC-34 | Booking Lifecycle | NgocPA | Staff | Complete booking | Done | 2026-05-10 | Medium | Staff completes the booking after the customer has used the field. | Only checked-in bookings can be completed; completion contributes to membership progress.
UC-35 | Booking Lifecycle | NgocPA | Staff | Mark no-show | Done | 2026-05-10 | Medium | Staff marks a booking as no-show when the customer does not arrive. | Only eligible confirmed bookings can be marked no-show. No-show does not count toward membership progress.
UC-36 | Booking Lifecycle | NgocPA | Staff | Handle booking conflict | Done | 2026-05-10 | High | Staff handles conflicts when a field problem or unavailable slot affects existing bookings. | Conflict handling reuses reschedule, cancellation, refund, issue, and notification tools rather than introducing a separate duplicate flow.
UC-37 | Payment Gateway, Refund & Invoice | AnNP | Customer/Staff | View checkout summary | Done | 2026-05-10 | Medium | Customer or staff views the booking cost before payment. | Summary includes field, services, promotion and membership discounts, total, deposit, paid amount, and remaining balance in USD.
UC-38 | Payment Gateway, Refund & Invoice | AnNP | Customer/Staff | Choose payment option | Done | 2026-05-10 | Medium | Customer chooses deposit/full online payment; Staff chooses the cash amount for a walk-in booking. | Customer chooses deposit/full for online checkout. Staff chooses cash deposit/full for a walk-in; Admin has no checkout flow.
UC-39 | Payment Gateway, Refund & Invoice | AnNP | Customer | Pay deposit/full amount via online payment sandbox | Done | 2026-05-10 | High | Customer pays the required deposit or full amount using an online payment sandbox. | PayPal Sandbox is customer-only. Server-side Orders v2 create/capture validates amount and USD currency before confirmation.
UC-40 | Payment Gateway, Refund & Invoice | AnNP | System | Capture/confirm online payment | Done | 2026-05-10 | High | The system confirms the result of an online payment transaction. | Provider order/capture identifiers, transaction code, amount, method, and status are persisted and reconciled into booking/invoice state.
UC-41 | Payment Gateway, Refund & Invoice | AnNP | Staff/System | Confirm remaining payment | Done | 2026-05-10 | Medium | Staff records the remaining on-site cash balance after a deposit. | Staff records the remaining balance as an on-site cash payment. Staff/Admin cannot initiate customer PayPal checkout.
UC-42 | Payment Gateway, Refund & Invoice | AnNP | System/Customer | Handle failed/expired payment | Done | 2026-05-10 | Medium | The system handles failed or expired payments. | Failed payments remain visible; the timeout scheduler expires aged unpaid holds and releases their slots.
UC-43 | Payment Gateway, Refund & Invoice | AnNP | Customer/Staff | View payment history | Done | 2026-05-10 | Low | A user views payment and transaction history. | History returns real persisted cash/PayPal transactions, including partial/full-refund status, and is restricted by role/booking ownership.
UC-44 | Payment Gateway, Refund & Invoice | AnNP | System/Staff | Generate booking invoice | Done | 2026-05-10 | Medium | The system generates an invoice for the booking. | Invoice totals include field, services, discounts, paid, remaining, and refund amounts and are updated after permitted booking edits.
UC-45 | Payment Gateway, Refund & Invoice | AnNP | Customer/Staff | View invoice/payment status | Done | 2026-05-10 | Low | A user views invoice and payment status for a booking. | Billing detail exposes invoice status, paid/remaining/refunded amounts, and transaction history.
UC-46 | Payment Gateway, Refund & Invoice | AnNP | Staff/Admin/System | Process online refund | Done | 2026-05-10 | High | Staff or Admin approves an eligible refund and the system submits an online provider refund. | After Staff/Admin approval, PayPal Payments v2 refunds the captured payment by capture ID with idempotency. Only provider COMPLETED is final; gross, exact processor fee, provider net, and refunded amount remain separately auditable.
UC-47 | Payment Gateway, Refund & Invoice | AnNP | Customer/Staff/Admin | Manage refund requests | Done | 2026-05-10 | Medium | A customer requests an eligible refund; Staff or Admin reviews and processes it. | The booking owner submits the request. Staff/Admin can approve/reject, submit/retry a PayPal refund, or explicitly record completion of a cash refund.
UC-48 | Payment Gateway, Refund & Invoice | AnNP | Admin | Configure deposit rules | Done | 2026-05-10 | Medium | Admin configures deposit rules. | Admin maintains the default online booking deposit percentage in system settings.
UC-49 | Payment Gateway, Refund & Invoice | AnNP | Admin | Configure cancellation/refund policy | Done | 2026-05-10 | Medium | Admin configures cancellation and refund policy. | Admin maintains before-24-hour and same-day refund percentages in Policies.
UC-50 | Promotion, Membership, Notification & Report | AnPTT | Customer/Guest | View active promotions | Done | 2026-05-10 | Low | Customer or guest views active promotions and event sales. | Guests/customers see only active campaigns, including banner image and eligibility period.
UC-51 | Promotion, Membership, Notification & Report | AnPTT | Admin | Manage promotion campaigns | Done | 2026-05-10 | High | Admin creates, updates, enables, or disables promotion campaigns. | Only Admin creates, updates, activates/deactivates, and uploads campaign banners.
UC-52 | Promotion, Membership, Notification & Report | AnPTT | Customer/System | Apply promotion to booking | Done | 2026-05-10 | High | Customer applies a promotion during checkout. | One promotion code per booking. Eligibility covers date, usage, minimum amount, field type, service, membership, day, and time.
UC-53 | Promotion, Membership, Notification & Report | AnPTT | Customer | View membership progress | Done | 2026-05-10 | Medium | A customer views membership progress under the configured lifetime, monthly, or weekly rule. | Progress uses the active level rule: lifetime count, current-month count, or consecutive qualifying weeks. Cancelled, rejected, expired, and no-show bookings do not count.
UC-54 | Promotion, Membership, Notification & Report | AnPTT | Admin | Manage membership rules | Done | 2026-05-10 | Medium | An admin manages membership qualification rules and benefits. | Admin configures lifetime, monthly, or consecutive-week qualification rules together with completed-booking thresholds, ordering, status, and discount benefits.
UC-55 | Promotion, Membership, Notification & Report | AnPTT | Customer/Guest | View membership benefits | Done | 2026-05-10 | Low | Customer or guest views the benefits of each membership level. | Active membership levels and their discount/benefit descriptions are customer-visible.
UC-56 | Promotion, Membership, Notification & Report | AnPTT | System | Send booking confirmation notification | Done | 2026-05-10 | Medium | The system sends a notification when a booking is confirmed. | Booking creation/confirmation produces an in-app notification.
UC-57 | Promotion, Membership, Notification & Report | AnPTT | System | Send booking reminder notification | Done | 2026-05-10 | Medium | The system reminds the customer before the booking starts. | A configurable scheduler sends one reminder before the booking start time.
UC-58 | Promotion, Membership, Notification & Report | AnPTT | System | Send cancellation/refund notification | Done | 2026-05-10 | Medium | The system sends a notification when a booking is cancelled or refunded. | Cancellation and completed refund status changes produce in-app notifications.
UC-59 | Promotion, Membership, Notification & Report | AnPTT | Admin | View revenue report | Done | 2026-05-10 | Medium | Admin views the revenue report. | Admin report includes gross collected, exact PayPal processor fees, provider net, completed refunds, net revenue, field/service value, discounts, and booking totals in USD.
UC-60 | Promotion, Membership, Notification & Report | AnPTT | Admin | View booking report | Done | 2026-05-10 | Medium | Admin views booking statistics. | Admin report includes lifecycle counts, peak start time, and field utilization.
UC-61 | Promotion, Membership, Notification & Report | AnPTT | Admin | View customer activity report | Done | 2026-05-10 | Medium | Admin views customer behavior and activity statistics. | Admin report includes returning/tracked customers, top customer activity, and membership distribution.
UC-62 | Promotion, Membership, Notification & Report | AnPTT | Customer | Ask availability assistant | Deferred | 2026-05-10 | High | A signed-in customer asks Gemini to interpret a natural-language field request; all displayed availability remains grounded in live GoalZone data. | Implementation is present and uses Gemini 3.6 Flash for criteria extraction and concise wording. Deployment remains Deferred until GEMINI_API_KEY is configured and one external smoke test passes; missing configuration correctly returns HTTP 503.
UC-63 | Promotion, Membership, Notification & Report | AnPTT | Customer/System | Get ranked available slot suggestions | Done | 2026-05-10 | Medium | The system deterministically ranks live available slots and hands the selected result to the normal booking checkout. | Authoritative UC-63 ranking uses live availability, preferred time, budget, field type, membership context, and eligible campaigns. It works independently of Gemini, explains each result, transfers the selected slot, and revalidates at checkout.

## Contribution
Name | Role | Tasks/Modules Assigned | Contribution %
BonVT | Member | Account & Customer Status | 20%
NgocPA | Member | Booking Lifecycle | 20%
BaoNG | Member | Field, Slot, Service & Issue Management | 20%
AnNP | Member | Payment Gateway, Refund & Invoice | 20%
AnPTT | Member | Promotion, Membership, Notification & Report | 20%