## Backlog
UC ID | Feature | Owner | Actor | Use Case | Status | Deadline | Difficulty | Description | Notes
UC-01 | Account onboarding | BonVT | Guest | Register account | Done | 2026-05-10 | Medium | A guest creates a customer account. | Unique email and phone are enforced. Customer is the default role. SMTP email verification is an extension of registration.
UC-02 | Authentication | BonVT | Guest/User | Login | Done | 2026-05-10 | Medium | A user logs in to the system. | Email is normalized before lookup. Only active accounts may sign in; locking an account revokes existing JWTs.
UC-03 | Authentication | BonVT | User | Logout | Done | 2026-05-10 | Low | A user logs out of the system. | Logout revokes the active JWT so the same token cannot be reused.
UC-04 | Profile management | BonVT | User | Manage personal profile | Done | 2026-05-10 | Medium | A user views and updates their personal information. | Users may update only their own name, phone, and address. Role and account status are administrative data and are never editable from the personal profile.
UC-05 | Credential security | BonVT | User | Change password | Done | 2026-05-10 | Medium | A logged-in user changes their password. | The current password is required, the replacement must satisfy password rules, and each user may change only their own password.
UC-06 | Account recovery | BonVT | Guest/User | Recover password | Done | 2026-05-10 | Medium | A guest securely recovers access to an account. | Requesting a link, validating the one-hour single-use token, and setting the replacement password are phases of one recovery goal.
UC-07 | Customer account administration | BonVT | Admin | View customer accounts | Done | 2026-05-10 | Low | An admin lists Customer accounts and opens business-facing account and activity information. | The UI shows name, contact, status, booking code, field, issue description/status, and dates when relevant. Raw database IDs are transport keys and are not presented as useful content.
UC-08 | Customer account administration | BonVT | Admin | Lock/unlock customer account | Done | 2026-05-10 | Medium | An admin locks or restores a Customer account when an access-control reason exists. | Lock requires a reason, changes status, increments authVersion, revokes existing JWTs, and sends email/in-app notification. Unlock restores active status and notifies the Customer.
UC-09 | Staff account administration | BonVT | Admin | Manage staff accounts | Done | 2026-05-10 | Medium | An admin creates and maintains Staff identity/status; Staff receives an invitation to set their own password. | Admin creates and updates Staff identity/status only. A one-hour setup link is emailed so Staff owns the password; Admin cannot set or replace it.
UC-10 | Customer activity | BonVT | Admin | View customer activity | Done | 2026-05-10 | Low | Admin views customer activity information. | This is an operational drill-down for one Customer, distinct from the aggregate Customer activity report. Business context is shown instead of raw IDs.
UC-11 | Field catalogue | BaoNG | Guest/Customer | View field list | Done | 2026-05-10 | Low | A guest or customer views the list of available football fields. | Only active fields are customer-visible. Field type, location, surface, capacity, image, and pricing context are shown.
UC-12 | Field catalogue | BaoNG | Guest/Customer | View field detail | Done | 2026-05-10 | Low | A guest or customer views detailed information about a selected field. | Includes uploaded image, location, surface, capacity, price range/bands, and active add-ons. Reviews/ratings are explicitly out of scope.
UC-13 | Availability search | BaoNG | Guest/Customer | Search available fields by date/time | Done | 2026-05-10 | High | The system automatically materializes and searches bookable slots for a selected date. | Search materializes an in-horizon date on demand and returns only slots with an active matching price rule. No fallback or magic price is used.
UC-14 | Field management | BaoNG | Admin | Manage football fields | Done | 2026-05-10 | Medium | An admin creates, updates, enables, or disables football fields. | Admin creates/updates fields, changes active status, and uploads JPEG/PNG/WebP/GIF images up to 5 MB.
UC-15 | Field pricing | BaoNG | Admin | Manage field pricing by time range | Done | 2026-05-10 | High | An admin configures field prices by time range and day type. | Pricing supports weekday/weekend and time bands. The applicable price is resolved for each generated slot.
UC-16 | Slot generation rules | BaoNG | Admin | Configure slot generation rules | Done | 2026-05-10 | High | An admin configures how the rolling field-slot calendar is generated. | Opening time, closing time, slot duration, and a 1–90 day horizon are validated together. A rule change rebuilds only unbooked available auto-generated rows.
UC-17 | Slot exceptions | BaoNG | Staff | Block/unblock field slots | Done | 2026-05-10 | High | Staff blocks or unblocks exceptional field periods for operational reasons. | Block covers every overlapping slot, rejects active-booking conflicts, and may record a future exception. Ordinary availability never requires a manual Add Slot action.
UC-18 | Operations calendar | BaoNG | Staff | View field operation calendar | Done | 2026-05-10 | Medium | Staff views the automatically materialized operation calendar by field and date. | Opening the daily view first materializes an in-horizon date from Admin rules, then shows available, blocked, and booked slots with booking/customer context. Block/Unblock remains the exception workflow.
UC-19 | Extra-service catalogue | BaoNG | Admin | Manage extra services | Done | 2026-05-10 | Medium | An admin manages extra services such as ball rental, bibs, drinks, or referee service. | Admin creates, updates, activates, and deactivates priced rental, sale, or staff services.
UC-20 | Booking add-ons | BaoNG | Customer/Staff | Add extra services to booking | Done | 2026-05-10 | Medium | Customer or staff adds extra services to a booking. | Service availability is included server validation. Positive integer quantities, active status, limits, and overlapping shared stock are checked before persistence.
UC-21 | Booking add-ons | BaoNG | Customer/Staff | Update extra services before check-in | Done | 2026-05-10 | Medium | The owning customer or Staff updates selected extra services before check-in. | The owning Customer or Staff may edit before check-in. Services, discounts, balance/refund delta, promotion reservation, and invoice are recalculated atomically.
UC-22 | Issue management | BaoNG | Customer/Staff | Report field/service issue | Done | 2026-05-10 | Medium | Customer or staff reports a field or service issue. | The authenticated Customer or Staff member is always the reporter. Title/description are required and booking/field/service links must be consistent.
UC-23 | Issue management | BaoNG | Staff | Resolve field/service issue | Done | 2026-05-10 | Medium | Staff handles and updates the issue status. | Staff handles an issue under their own identity. Valid flow is open -> in progress -> resolved/rejected; closed issues cannot be reopened.
UC-24 | Booking creation | NgocPA | Customer | Create online booking | Done | 2026-05-10 | High | A customer creates an online field booking. | Customer-only flow validates availability, priced slot, selected services, promotion/membership rules, payment hold, and PayPal Sandbox checkout.
UC-25 | Booking creation | NgocPA | Staff | Create walk-in booking | Done | 2026-05-10 | Medium | Venue Staff creates a walk-in booking for a matched Customer account or a first-time visitor identified by name and phone. | Search by phone/email first. If no account matches, store guest name and phone (email optional) on the booking without creating an account. Guest walk-ins have no membership, PayPal checkout, or account notification. Pay later stays pending; deposit/full cash is atomic.
UC-26 | Booking details | NgocPA | Customer/Staff | View booking detail | Done | 2026-05-10 | Low | A user views detailed information about a booking. | Detail includes slot, services, promotion, payments, invoice, and refunds. Access is protected by role and ownership.
UC-27 | Booking history | NgocPA | Customer | View my bookings | Done | 2026-05-10 | Low | A customer views their current and past bookings. | The Customer Account workspace shows current/past bookings and their billing details.
UC-28 | Booking calendar | NgocPA | Staff | View booking calendar | Done | 2026-05-10 | Medium | Staff views bookings by field and date. | The Staff workspace provides a daily booking queue/calendar and selected-booking operation controls.
UC-29 | Booking rescheduling | NgocPA | Customer/Staff | Reschedule booking | Done | 2026-05-10 | High | Customer or Staff moves a booking to another available field slot. | Customer or Staff may reschedule a pending/confirmed booking only before its original start. Destination availability, price, add-ons, discounts, and balance are recalculated.
UC-30 | Booking cancellation | NgocPA | Customer/Staff | Cancel booking | Done | 2026-05-10 | High | A booking is cancelled according to the cancellation policy. | Preview is the mandatory first step of this use case. Cancellation is allowed only before start; policy fee/refundable amount is stored and any refund remains auditable.
UC-31 | Venue operations | NgocPA | Staff | Check in booking | Done | 2026-05-10 | Medium | Staff confirms that the customer has arrived at the venue. | Venue Staff may check in a confirmed booking from 30 minutes before start after the required deposit is paid.
UC-32 | Venue operations | NgocPA | Staff | Complete booking | Done | 2026-05-10 | Medium | Staff completes the booking after the customer has used the field. | Venue Staff may complete only a started, checked-in booking with zero remaining balance; completion contributes to membership progress.
UC-33 | Venue operations | NgocPA | Staff | Mark no-show | Done | 2026-05-10 | Medium | Staff marks a booking as no-show when the customer does not arrive. | Venue Staff may record no-show only from 15 minutes after start. No-show does not count toward membership progress.
UC-34 | Checkout | AnNP | Customer/Staff | View checkout summary | Done | 2026-05-10 | Medium | Customer or staff views the booking cost before payment. | Anonymous quotes contain no membership pricing. Customer-specific pricing requires the signed-in owner; Staff may quote a selected walk-in Customer.
UC-35 | Checkout | AnNP | Customer/Staff | Choose payment option | Done | 2026-05-10 | Medium | Customer chooses deposit/full online payment; Staff chooses the cash amount for a walk-in booking. | Customer chooses deposit/full for online checkout. Staff chooses cash deposit/full for a walk-in; Admin has no checkout flow.
UC-36 | Online payment | AnNP | Customer | Pay online via PayPal Sandbox | Done | 2026-05-10 | High | Customer pays the required deposit or full amount using an online payment sandbox. | Customer creates and approves a PayPal Sandbox order. Server capture, amount/currency verification, idempotency, persistence, and automatic booking confirmation are included steps.
UC-37 | Counter payment | AnNP | Staff | Confirm remaining payment | Done | 2026-05-10 | Medium | Staff records the remaining on-site cash balance after a deposit. | Staff records a real on-site cash payment against a remaining balance. Staff/Admin cannot initiate Customer PayPal checkout.
UC-38 | Payment recovery | AnNP | Customer/PayPal/Scheduler | Handle failed/expired payment | Done | 2026-05-10 | Medium | The system handles failed or expired payments. | Provider failure remains visible and retryable. The scheduler expires aged unpaid holds, releases slots and promotion capacity, and notifies the Customer.
UC-39 | Payment records | AnNP | Customer/Staff | View payment history | Done | 2026-05-10 | Low | A user views payment and transaction history. | History returns real persisted cash/PayPal transactions, including partial/full-refund status, and is restricted by role/booking ownership.
UC-40 | Billing status | AnNP | Customer/Staff | View invoice/payment status | Done | 2026-05-10 | Low | A user views invoice and payment status for a booking. | The system-maintained invoice is a booking/payment postcondition. This view exposes field/services/discounts, paid, remaining, refunded, status, and persisted transactions.
UC-41 | Refund management | AnNP | Staff/Admin/PayPal | Process online refund | Done | 2026-05-10 | High | Staff or Admin approves an eligible refund and the system submits an online provider refund. | After Staff/Admin approval, PayPal Payments v2 refunds the captured payment with idempotency. Only provider COMPLETED is final; gross, fee, net, and refund stay auditable.
UC-42 | Refund management | AnNP | Customer/Staff/Admin | Manage refund requests | Done | 2026-05-10 | Medium | A customer requests an eligible refund; Staff or Admin reviews and processes it. | The booking owner supplies reason and eligible amount. Authenticated Staff/Admin is the reviewer identity; client-supplied actor IDs are rejected.
UC-43 | Booking policies | AnNP | Admin | Configure deposit rules | Done | 2026-05-10 | Medium | Admin configures deposit rules. | Admin maintains the default online booking deposit percentage in system settings.
UC-44 | Booking policies | AnNP | Admin | Configure cancellation/refund policy | Done | 2026-05-10 | Medium | Admin configures cancellation and refund policy. | Admin maintains before-24-hour and same-day refund percentages in Policies.
UC-45 | Promotions | AnPTT | Customer/Guest | View active promotions | Done | 2026-05-10 | Low | Customer or guest views active promotions and event sales. | Guests/customers see only active campaigns, including banner image and eligibility period.
UC-46 | Promotions | AnPTT | Admin | Manage promotion campaigns | Done | 2026-05-10 | High | Admin creates, updates, enables, or disables promotion campaigns. | Only Admin creates, updates, activates/deactivates, and uploads campaign banners.
UC-47 | Promotions | AnPTT | Customer/System | Apply promotion to booking | Done | 2026-05-10 | High | Customer applies a promotion during checkout. | Eligibility and discount are snapshotted. Pending holds reserve campaign capacity; confirmation consumes it, while cancellation/expiry releases it.
UC-48 | Membership | AnPTT | Customer | View membership progress | Done | 2026-05-10 | Medium | A customer views membership progress under the configured lifetime, monthly, or weekly rule. | Progress uses the active level rule: lifetime count, current-month count, or consecutive qualifying weeks. Cancelled, rejected, expired, and no-show bookings do not count.
UC-49 | Membership | AnPTT | Admin | Manage membership rules | Done | 2026-05-10 | Medium | An admin manages membership qualification rules and benefits. | Admin configures lifetime, monthly, or consecutive-week qualification rules together with completed-booking thresholds, ordering, status, and discount benefits.
UC-50 | Membership | AnPTT | Customer/Guest | View membership benefits | Done | 2026-05-10 | Low | Customer or guest views the benefits of each membership level. | Active membership levels and their discount/benefit descriptions are customer-visible.
UC-51 | Notifications | AnPTT | Customer | Send booking confirmation notification | Done | 2026-05-10 | Medium | The system sends a notification when a booking is confirmed. | A valid booking confirmation event produces one in-app notification for the receiving Customer.
UC-52 | Notifications | AnPTT | Scheduler/Customer | Send booking reminder notification | Done | 2026-05-10 | Medium | The system reminds the customer before the booking starts. | A configurable scheduler sends at most one reminder in the configured window before a qualifying booking starts.
UC-53 | Notifications | AnPTT | Customer | Send cancellation/refund notification | Done | 2026-05-10 | Medium | The system sends a notification when a booking is cancelled or refunded. | Cancellation and completed refund events produce in-app notifications for the affected Customer.
UC-54 | Reporting | AnPTT | Admin | View revenue report | Done | 2026-05-10 | Medium | Admin views the revenue report. | Revenue uses persisted payments/refunds. Cancelled, rejected, and expired bookings are excluded from booked commercial value.
UC-55 | Reporting | AnPTT | Admin | View booking report | Done | 2026-05-10 | Medium | Admin views booking statistics. | Utilization and peak demand count only confirmed, checked-in, completed, and no-show bookings; terminal invalid rows do not inflate usage.
UC-56 | Reporting | AnPTT | Admin | View customer activity report | Done | 2026-05-10 | Medium | Admin views customer behavior and activity statistics. | Aggregate report uses qualifying bookings inside the selected period. It is distinct from the single-Customer operational drill-down in UC-10.

## Contribution
Name | Role | Feature areas owned | Contribution %
BonVT | Member | Identity, access & customer administration (UC-01–UC-10) | 20%
NgocPA | Member | Booking lifecycle & venue operations (UC-24–UC-33) | 20%
BaoNG | Member | Fields, slots, add-ons & issues (UC-11–UC-23) | 20%
AnNP | Member | Checkout, payment, refunds & policies (UC-34–UC-44) | 20%
AnPTT | Member | Promotions, membership, notifications & reports (UC-45–UC-56) | 20%